## 2025.1
Documentation | Section | Sub-sections | Writer | Comments | Subject Matter Expert/Engineering | Schedule: See schedule tab | Doc Plan Completed * Yes\No * Reviewer Signoff (include names and dates): -Developer -Apps -QA -Marketing | Reviewed and Approvd (Done) - Give date. -Developer -Apps -QA -Marketing | Estimated Time/ Actual time | color | completion | Comments Green = updates ready for QA to review Yellow = In progress, needs to update Grey = Not needed for curent release White = no changes from existing/ no update needed Orange = updates pushed out to next release
Online Help User Guides | Getting Started with Radiant | Introduction | Ruby-Ann Daliva | Update text from 2024.2 to 2025.1 | [5 empty] | yellow | 50%
Online Help User Guides | Getting Started with Radiant | Tutorials | Ruby-Ann Daliva | Updated URLs for 2025.1 release | [5 empty] | yellow | 50%
Online Help User Guides | Getting Started with Radiant | User Guides | Ruby-Ann Daliva | Updated URLs for 2025.1 release | [5 empty] | yellow | 50%
Online Help User Guides | Getting Started with Radiant | Getting Help | [7 empty] | white | 30%
Online Help User Guides | Getting Started with Radiant | Debugging the Software License | [7 empty] | white | 30%
Online Help User Guides | Getting Started with Radiant | Copyright, Trademarks, and Disclaimers | [7 empty] | white | 30%
Online Help User Guides | Managing Projects | Introduction | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Managing Projects | Running the Radiant Software | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Managing Projects | Creating a New Project | [7 empty] | white | 30%
Online Help User Guides | Managing Projects | Modifying a Project | [7 empty] | white | 30%
Online Help User Guides | Managing Projects | Importing Lattice Diamond Projects | [7 empty] | white | 30%
Online Help User Guides | Managing Projects | Targeting a Device | [7 empty] | white | 30%
Online Help User Guides | Managing Projects | Viewing Project Properties | [7 empty] | white | 30%
Online Help User Guides | Managing Projects | Saving Project Files | Adel Jambalos | [6 empty] | white | 30%
Online Help User Guides | Managing Projects | Managing Project Sources | Ave Manriquez | [6 empty] | white | 30%
Online Help User Guides | Managing Projects | Working with Implementations | [7 empty] | white | 30%
Online Help User Guides | Managing Projects | Using Strategies | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Managing Projects | Analyzing a Design | Adel Jambalos | [6 empty] | white | 30%
Online Help User Guides | Managing Projects | Running Processes | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Managing Projects | Clearing Tool Memory | [7 empty] | white | 30%
Online Help User Guides | Managing Projects | Setting Options for Synthesis and Simulation | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Managing Projects | Finding Results | [7 empty] | white | 30%
Online Help User Guides | Managing Projects | Viewing Logs and Reports | Ave Manriquez | •ERD-05.08 (DNG-22491) – Request for adding "percentage" view in Report Summary and Run Manager --05/09/2025: Documentation is done, Manish has reviewed and approved updates. Changes here: User Guides > Managing Projects > Viewing Logs and Reports •ERD-05.10 (DNG-21175) – Enhancement Request - Breakdowns of Runtime for Different Compilation Stage --03/27/2025: In Progress. Per Manish, this is not yet implemented in Radiant. --05/05/2025: Done. Added to User Guides > Managing Projects > Viewing Logs and Reports section. •ERD-10.02 (DNG-22646) – Report parameters on an entity with generics to show what has been passed --03/27/2025: In Progress. Verifying with Alka if this has been implemented in Radiant. --04/03/2025: Followed up with Alka. --04/07/2025: Added content to User Guides > Managing Projects > Viewing Logs and Reports and sent to Alka for review. | Joginder Singh |  |  |  |  | green | 100%
Online Help User Guides | Managing Projects | Viewing Logs and Reports | Verna Deatras | •ERD-05.08 (DNG-22491) – Request for adding "percentage" view in Report Summary and Run Manager --05/09/2025: Documentation is done, Manish has reviewed and approved updates. Changes here: User Guides > Managing Projects > Viewing Logs and Reports •ERD-05.10 (DNG-21175) – Enhancement Request - Breakdowns of Runtime for Different Compilation Stage --03/27/2025: In Progress. Per Manish, this is not yet implemented in Radiant. --05/05/2025: Done. Added to User Guides > Managing Projects > Viewing Logs and Reports section. •ERD-10.02 (DNG-22646) – Report parameters on an entity with generics to show what has been passed --03/27/2025: In Progress. Verifying with Alka if this has been implemented in Radiant. --04/03/2025: Followed up with Alka. --04/07/2025: Added content to User Guides > Managing Projects > Viewing Logs and Reports and sent to Alka for review. | Joginder Singh |  |  |  |  | green | 100%
Online Help User Guides | Managing Projects | Setting Tool and Environment Options | [7 empty] | white | 30%
Online Help User Guides | Managing Projects | Introduction | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Managing Projects | HDL Design Entry | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Managing Projects | Block-Based Design - Using Macro Blocks | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Managing Projects | Packaging IP Using Radiant IP Packager | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Managing Projects | Designing with Soft IP, Modules, and PMI | Ruby-Ann Daliva |  | Joginder Singh |  |  |  |  | white | 30%
Online Help User Guides | Securing the Design | Introduction | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Securing the Design | HDL File Encryption Steps | [7 empty] | white | 30%
Online Help User Guides | Securing the Design | Synthesizing Encrypted IP | [7 empty] | white | 30%
Online Help User Guides | Securing the Design | Cross-probing in Encrypted Design | [7 empty] | white | 30%
Online Help User Guides | Securing the Design | Secure Objects in the Design | Adel Jambalos |  | Pradeep Lenka |  |  |  |  | white | 30%
Online Help User Guides | Securing the Design | Securing the Bitstream | Adel Jambalos |  | Cindy Lee/Michael Schneider |  |  |  |  | white | 30%
Online Help User Guides | Simulating the Design | Introduction | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Simulating the Design | Simulation in the Radiant Software | Verna Deatras |  | John Wamba |  |  |  |  | white | 30%
Online Help User Guides | Simulating the Design | Timing Simulation | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Simulating the Design | Third-Party Simulators | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Applying Design Constraints | Introduction | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Applying Design Constraints | Unified Constraint Flow | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Applying Design Constraints | Understanding Implications of Radiant Constraint Flows | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Applying Design Constraints | Applying Differential Signal Design Constraints | [7 empty] | white | 30%
Online Help User Guides | Applying Design Constraints | Timing and Physical Constraints | Ruby-Ann Daliva | [6 empty] | white | 30%
Online Help User Guides | Applying Design Constraints | Checking Constraint Coverage | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Applying Design Constraints | Migrating from Former Lattice Diamond Preferences | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Applying Design Constraints | Migrating Pin Assignments | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Applying Design Constraints | Using Radiant Software Pre-Synthesis Constraints | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Applying Design Constraints | Constraint Propagation | Adel Jambalos | •ERD-09.07 (DNG-20110) – Simplify the Process of Setting Virtual Pins [Verna] -- 03/31/25: In Progress. Contacted SMEs to provide strategy ID and description. [Verna] -- 04/02/25: Added strategy ID and description to Strategies Reference Guide. [Verna] -- 04/03/25: Added to Tool and Other Enhancements. •ERD-17.04 (DNG-22642) – Power calculator should make user entry of IO banks optional -ECN_YES_TO_DEFER •ERD-05.03 (DNG-22521) – TCE: Request for 'Copy Constraint' to copy text into global buffer to enable paste (CTRL+V) in other applications--05/22/2025: Approved and updated to Perforce | ERD-05.03 - Joginder Singh ERD-05.03 - Joginder Singh ERD-17.04 - Ian Kwan |  |  |  |  | yellow | 50%
Online Help User Guides | Applying Design Constraints | Constraint Propagation | Verna Deatras | •ERD-09.07 (DNG-20110) – Simplify the Process of Setting Virtual Pins [Verna] -- 03/31/25: In Progress. Contacted SMEs to provide strategy ID and description. [Verna] -- 04/02/25: Added strategy ID and description to Strategies Reference Guide. [Verna] -- 04/03/25: Added to Tool and Other Enhancements. •ERD-17.04 (DNG-22642) – Power calculator should make user entry of IO banks optional -ECN_YES_TO_DEFER •ERD-05.03 (DNG-22521) – TCE: Request for 'Copy Constraint' to copy text into global buffer to enable paste (CTRL+V) in other applications--05/22/2025: Approved and updated to Perforce | ERD-05.03 - Joginder Singh ERD-05.03 - Joginder Singh ERD-17.04 - Ian Kwan |  |  |  |  | yellow | 50%
Online Help User Guides | Applying Design Constraints | Constraint Propagation | Ruby-Ann Daliva | •ERD-09.07 (DNG-20110) – Simplify the Process of Setting Virtual Pins [Verna] -- 03/31/25: In Progress. Contacted SMEs to provide strategy ID and description. [Verna] -- 04/02/25: Added strategy ID and description to Strategies Reference Guide. [Verna] -- 04/03/25: Added to Tool and Other Enhancements. •ERD-17.04 (DNG-22642) – Power calculator should make user entry of IO banks optional -ECN_YES_TO_DEFER •ERD-05.03 (DNG-22521) – TCE: Request for 'Copy Constraint' to copy text into global buffer to enable paste (CTRL+V) in other applications--05/22/2025: Approved and updated to Perforce | ERD-05.03 - Joginder Singh ERD-05.03 - Joginder Singh ERD-17.04 - Ian Kwan |  |  |  |  | yellow | 50%
Online Help User Guides | Applying Design Constraints | Using Radiant Tools | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Applying Design Constraints | Applying Radiant Software Physical Constraints | Verna Deatras | •ERD-08.02 (DNG-13005) – AVANT_EAPR_AE_EVAL: Request for guided Bounding BOX generation 04/08/2025 -- In Progress. Updating "User Guides > Applying Design Constraints > Applying Radiant Software Physical Constraints > Setting Port, Net, and Cell Attributes > Creating GROUPs" section. 04/10/2025-- Done. Updated "User Guides > Applying Design Constraints > Applying Radiant Software Physical Constraints > Setting Port, Net, and Cell Attributes > Creating GROUPs" section. Sent to Deepak and Sukruth for review --Added to Tool and Other Enhancements section of the release notes. | [5 empty] | green | 100%
Online Help User Guides | Applying Design Constraints | Constraint Conflict Resolution | [7 empty] | white | 30%
Online Help User Guides | Applying Design Constraints | Checking Design Rules | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Applying Design Constraints | Analyzing SSO | [7 empty] | white | 30%
Online Help User Guides | Applying Design Constraints | Exporting Pin Files | [7 empty] | white | 30%
Online Help User Guides | Implementing the Design | Introduction | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Implementing the Design | Synthesizing the Design | [7 empty] | white | 30%
Online Help User Guides | Implementing the Design | Mapping | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Implementing the Design | Place and Route | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Implementing the Design | Bit Generation | Adel Jambalos | [6 empty] | white | 30%
Online Help User Guides | Implementing the Design | (no subsection) | [7 empty] | white | 30%
Online Help User Guides | Implementing the Design | SEI Editor | [7 empty] | white | 30%
Online Help User Guides | Using Incremental Design Flow | Running the Incremental Design Flow | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Analyzing Static Timing | Introduction | [7 empty] | white | 30%
Online Help User Guides | Analyzing Static Timing | Options for Timing Analysis Reports | Adel Jambalos | [6 empty] | white | 30%
Online Help User Guides | Analyzing Static Timing | Running Post-Synthesis Constraint Scenario Timing Reports | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Analyzing Static Timing | Reading Timing Analysis Reports | Adel Jambalos | [6 empty] | white | 30%
Online Help User Guides | Analyzing Static Timing | Using Timing Analyzer | Adel Jambalos |  | Gebre Gessese Jun Zhao |  |  |  |  | white | 30%
Online Help User Guides | Analyzing Static Timing | Using Timing Analyzer | Ave Manriquez |  | Gebre Gessese Jun Zhao |  |  |  |  | white | 30%
Online Help User Guides | Analyzing Static Timing | Using StandAlone Timing Analyzer | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Introduction | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Starting Power Calculator from Radiant | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Starting Power Calculator as a Stand-Alone Tool | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Running Power Calculator from the Tcl Console | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Power Analysis Design Flow | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Inputs | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Outputs | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Static and Dynamic Power Consumption | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Activity Factor Calculation | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Enable Factor Calculation | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Power Calculator Window Features | Ruby-Ann Daliva | •ERD -17.05 (DNG-22640) – Simplify the entry of PLL data in PWC--ECN_YES_TO_DEFER •ERD-17.07 (DNG-22519) – Power Calculator: Request for better clock frequency handling--ECN_YES_TO_DEFER •ERD-17.04 (DNG-22642) – Power calculator should make user entry of IO banks optional--ECN_YES_TO_DEFER | Ian Kwan |  |  |  |  | yellow | 50%
Online Help User Guides | Analyzing Power Consumption | Working with Power Calculator Files | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Entering Data | Adel Jambalos | •ERD-17.01 (DNG-22850) – Power Calculator DPM use model not clear-- 04/23/2025 added to Release Notes: Tools and Enhancements (DPM text is existing in Help) •ERD-17.02 (DNG-22745) – Power Calculator tool tip on 0 MHz clock entries--Jira status was moved to More Info and TBD for the release, discussion to defer to 2025.2 •ERD-17.08 (DNG-22406) – Request for Power Calculator to be verbose about why changes are rejected--ECN_YES_TO_DEFER | Ian Kwan |  |  |  |  | yellow | 50%
Online Help User Guides | Analyzing Power Consumption | Entering Data | Ruby-Ann Daliva | •ERD-17.01 (DNG-22850) – Power Calculator DPM use model not clear-- 04/23/2025 added to Release Notes: Tools and Enhancements (DPM text is existing in Help) •ERD-17.02 (DNG-22745) – Power Calculator tool tip on 0 MHz clock entries--Jira status was moved to More Info and TBD for the release, discussion to defer to 2025.2 •ERD-17.08 (DNG-22406) – Request for Power Calculator to be verbose about why changes are rejected--ECN_YES_TO_DEFER | Ian Kwan |  |  |  |  | yellow | 50%
Online Help User Guides | Analyzing Power Consumption | Calculator Sleep Mode | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Reverting to Calculation Mode | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Changing the Global Default Activity Factor | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Importing a Value Change Dump (.vcd) File | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Changing the Global Default Frequency Setting | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Estimating Resource Usage | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Estimating Routing Resource Usage | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Running Immediate Calculation | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Controlling Operating Temperature | Ruby-Ann Daliva | [6 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Controlling Power Options for Low-Power Devices | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Comparing Power Consumption Among Multiple Implementations | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Viewing and Printing Results | [7 empty] | white | 30%
Online Help User Guides | Analyzing Power Consumption | Device Support | [7 empty] | white | 30%
Online Help User Guides | Analyzing Signal Integrity | Introduction | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides |  | Lattice Semiconductor IBIS Models | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Programming the FPGA | Introduction | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Programming the FPGA | About the Programmer Window | [7 empty] | white | 30%
Online Help User Guides | Programming the FPGA | File Formats | [7 empty] | white | 30%
Online Help User Guides | Programming the FPGA | SPI Flash Support | [7 empty] | white | 30%
Online Help User Guides | Programming the FPGA | Using the Radiant Programmer | Verna Deatras |  | Nguyen Nguyen |  |  |  |  | white | 30%
Online Help User Guides | Programming the FPGA | Programmer Options | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Programming the FPGA | Programming and Configuring iCE40 Devices with Programmer | [7 empty] | white | 30%
Online Help User Guides | Programming the FPGA | Programming and Configuring LAV-AT, LFCPNX, LFD2NX, LFMNX, LFMXO5, LIFCL, MachXO3D, MachXO3L, MachXO3LF, UT24C or UT24CP Devices with Programmer | [7 empty] | white | 30%
Online Help User Guides | Programming the FPGA | Deploying the Design with Deployment Tool | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Programming the FPGA | Debugging SVF, STAPL, and VME Files | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Programming the FPGA | Download Debugger Options | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Programming the FPGA | Using Programming File Utility | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Programming the FPGA | Programming File Utility Options | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Testing and Debugging On-Chip | Introduction | Adel Jambalos |  | Andrew Lin, Pradeep Lenka |  |  |  |  | white | 30%
Online Help User Guides | Testing and Debugging On-Chip | About Reveal Logic Analysis | Adel Jambalos | •ERD-12.06 (DNG-22302) – Add Trace history Capability to Reveal [Adel] - 05-02-2025 Added feature to Help; Working with SME [Adel] - 06-04-2025 Done. Ready for QA verification : User Guides > Testing and Debugging On-Chip > Performing Logic Analysis > Viewing and Saving Waveforms. •ERD-12.03 (DNG-21502) – R2024.1_BETA_AE_EVA: make it so "min" and "max" can be selected [Adel] - 06-04-2025 Done. Ready for QA verification : User Guides > Testing and Debugging On-Chip > Performing Logic Analysis > Debugging with Reveal Controller > Virtual LED/Switch Console. •ERD 12.01 (DNG-22647) – Enhance the Reveal controller GUI for LEDs [Adel] - 06-04-2025 Done. Ready for QA verification. - User Guides > Testing and Debugging On-Chip > Performing Logic Analysis > Debugging with Reveal Controller > Virtual LED/Switch Console - User Guides > Testing and Debugging On-Chip > Creating Reveal Modules > Setting Up Virtual Switch/LED Settings > Assigning Colors to Virtual Switch/LED Signals | Andrew Lin, Pradeep Lenka |  |  |  |  | green | 100%
Online Help User Guides | Testing and Debugging On-Chip | Creating Reveal Modules | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Testing and Debugging On-Chip | Creating Reveal Modules | Ave Manriquez | [6 empty] | white | 30%
Online Help User Guides | Testing and Debugging On-Chip | Creating Reveal Modules | Adel Jambalos | [6 empty] | white | 30%
Online Help User Guides | Testing and Debugging On-Chip | Performing Logic Analysis | Adel Jambalos | •ERD-12.05 (DNG-22645) – External Memory Controller Debug [Adel] - 06-04-2025 Added feature to Help; Reviewed by Jacob; Need more info from SMEs | Andrew Lin, Pradeep Lenka |  |  |  |  | yellow | 50%
Online Help User Guides | Testing and Debugging On-Chip | Eye-Opening Monitor | [7 empty] | white | 30%
Online Help User Guides | Testing and Debugging On-Chip | Reveal Controller | Verna Deatras | [6 empty] | white | 30%
Online Help User Guides | Applying Engineering Change Orders | Introduction | [7 empty] | white | 30%
Online Help User Guides | Applying Engineering Change Orders | Editing sysIO Settings in ECO Editor | [7 empty] | white | 30%
Online Help User Guides | Applying Engineering Change Orders | Setting Memory Initialization Values in ECO Editor | [7 empty] | white | 30%
Online Help User Guides | Applying Engineering Change Orders | Running Design Rule Check | [7 empty] | white | 30%
Online Help Reference Guides | Strategy Reference Guide | Introduction | Verna Deatras | [6 empty] | white | 30%
Online Help Reference Guides | Strategy Reference Guide | Constraint Propagation Engine | [7 empty] | white | 30%
Online Help Reference Guides | Strategy Reference Guide | Synplify Pro Options | Verna Deatras | [6 empty] | white | 30%
Online Help Reference Guides | Strategy Reference Guide | LSE Options | Verna Deatras |  | Chin Hsiung, Venkat Rajappan, Peter Frey |  |  |  |  | white | 30%
Online Help Reference Guides | Strategy Reference Guide | (no subsection) | Verna Deatras | [6 empty] | white | 30%
Online Help Reference Guides | Strategy Reference Guide | Post-Synthesis Options | Ave Manriquez | [6 empty] | white | 30%
Online Help Reference Guides | Strategy Reference Guide | Post-Synthesis Timing Analysis Options | Adel Jambalos |  | Qinhai Zhang |  |  |  |  | white | 30%
Online Help Reference Guides | Strategy Reference Guide | Post-Synthesis Timing Analysis Options | Ave Manriquez |  | Qinhai Zhang |  |  |  |  | white | 30%
Online Help Reference Guides | Strategy Reference Guide | Map Design Options | Adel Jambalos | [6 empty] | white | 30%
Online Help Reference Guides | Strategy Reference Guide | Map Timing Analysis Options | Verna Deatras | [6 empty] | white | 30%
Online Help Reference Guides | Strategy Reference Guide | Place & Route Design Options | Adel Jambalos | [6 empty] | white | 30%
Online Help Reference Guides | Strategy Reference Guide | Place & Route Timing Analysis Options | Adel Jambalos | [6 empty] | white | 30%
Online Help Reference Guides | Strategy Reference Guide | IO Timing Analysis Options | [7 empty] | white | 30%
Online Help Reference Guides | Strategy Reference Guide | Timing Simulation Options | Ave Manriquez |  | Lennon Xi, Gebre |  |  |  |  | white | 30%
Online Help Reference Guides | Strategy Reference Guide | Bitstream Options | Adel Jambalos | [6 empty] | white | 30%
Online Help Reference Guides | Constraints Reference Guide | Introduction | Verna Deatras | [6 empty] | white | 30%
Online Help Reference Guides | Constraints Reference Guide | HDL Attributes | Verna Deatras |  | Joginder Singh |  |  |  |  | white | 30%
Online Help Reference Guides | Constraints Reference Guide | Lattice Synthesis Engine Constraints | Ave Manriquez |  | Gebre Gessese Jun Zhao |  |  |  |  | white | 30%
Online Help Reference Guides | Constraints Reference Guide | Lattice Synthesis Engine Constraints | Ruby-Ann Daliva |  | Gebre Gessese Jun Zhao |  |  |  |  | white | 30%
Online Help Reference Guides | Lattice Module Reference Guide | Introduction | Verna Deatras | [6 empty] | white | 30%
Online Help Reference Guides |  | Finding Modules in this Guide. | Verna Deatras | [6 empty] | white | 30%
Online Help Reference Guides | FPGA Libraries Reference Guide | Introduction | Verna Deatras | [6 empty] | white | 30%
Online Help Reference Guides | FPGA Libraries Reference Guide | Primitive Library - iCE40UP (iCE40 UltraPlus) | Verna Deatras | [6 empty] | white | 30%
Online Help Reference Guides | FPGA Libraries Reference Guide | Primitive Library - LAV-AT (Lattice Avant) | Ruby-Ann Daliva | [6 empty] | white | 30%
Online Help Reference Guides | FPGA Libraries Reference Guide | Primitive Library - LFCPNX (CertusPro-NX) / UT24CP (CertusPro-NX-RT) | Ave Manriquez | [6 empty] | white | 30%
Online Help Reference Guides | FPGA Libraries Reference Guide | Primitive Library - LFD2NX (Certus-NX) / UT24C (Certus-NX-RT) | Ruby-Ann Daliva | [6 empty] | white | 30%
Online Help Reference Guides | FPGA Libraries Reference Guide | Primitive Library - LFD2NX (Certus-NX) / UT24C (Certus-NX-RT) | Ave Manriquez | [6 empty] | white | 30%
Online Help Reference Guides | FPGA Libraries Reference Guide | Primitive Library - LFD2NX (Certus-NX) / UT24C (Certus-NX-RT) | Verna Deatras | [6 empty] | white | 30%
Online Help Reference Guides | FPGA Libraries Reference Guide | Primitive Library - LFMXO5 (Jedi-D6) | Ruby-Ann Daliva | [6 empty] | white | 30%
Online Help Reference Guides | FPGA Libraries Reference Guide | Primitive Library - LFMXO5 (Jedi-D6) | Ave Manriquez | [6 empty] | white | 30%
Online Help Reference Guides | FPGA Libraries Reference Guide | Primitive Library - LIFCL (CrossLink-NX) | Ave Manriquez | [6 empty] | white | 30%
Online Help Reference Guides | FPGA Libraries Reference Guide | Alphanumeric Primitives List | Ave Manriquez | •ERD-20.01 (DNG-23057) – Avant SEDC IP Enhancement Per discussion with Chang Kim Yong, this has no SW doc impact, only IP UG is affected. | Cindy Lee Michael Schneider |  |  |  |  | orange | 10%
Online Help Reference Guides | FPGA Libraries Reference Guide | Khronos EAPR | Verna Deatras |  | Cindy Lee Ian Kwan/Joginder Singh |  |  |  |  | white | 30%
Online Help Reference Guides | FPGA Libraries Reference Guide | DSP Inference Guide | [7 empty] | white | 30%
Online Help Reference Guides | FPGA Libraries Reference Guide | Synthesis Attributes | [7 empty] | white | 30%
Online Help Reference Guides | Command Line Reference Guide | Introduction | [7 empty] | white | 30%
Online Help Reference Guides | Command Line Reference Guide | Command Line Program Overview | [7 empty] | white | 30%
Online Help Reference Guides | Command Line Reference Guide | Command Line Basics | [7 empty] | white | 30%
Online Help Reference Guides | Command Line Reference Guide | Command Line Tool Usage | Verna Deatras | •ERD-13.01 (DNG-23102) – SSPI Command Line Tool 04/10/2025 -- In Progress. Contacted Nguyen and Chin Chuan for more info. 04/28/2025 -- Done. Added to Command Line Reference Guide. Sent to Sorabh for review. | Nguyen Nguyen |  |  |  |  | green | 100%
Online Help Reference Guides | Tcl Command Reference Guide | Introduction | Ave Manriquez |  | Qinhai Zhang |  |  |  |  | white | 30%
Online Help Reference Guides | Tcl Command Reference Guide | Introduction | Adel Jambalos |  | Qinhai Zhang |  |  |  |  | white | 30%
Online Help Reference Guides | Tcl Command Reference Guide | Introduction | Ruby-Ann Daliva |  | Qinhai Zhang |  |  |  |  | white | 30%
Online Help Reference Guides | Tcl Command Reference Guide | Introduction | Verna Deatras |  | Qinhai Zhang |  |  |  |  | white | 30%
Online Help Reference Guides | Tcl Command Reference Guide | Launching the Tcl Console | Ave Manriquez | •ERD-14.04 (DNG-22386) – Document the Radiant TCL console (radiantc) support for loading arguments 5/5/2025 -- In Progress. Updated the Launching the TCL Console section and Matt already reviewed the changes. Checked in 5/5/2025 | Joginder Singh |  |  |  |  | green | 100%
Online Help Reference Guides | Tcl Command Reference Guide | Running Radiant Tcl | Verna Deatras | •ERD-19.06 (DNG-22239) – Allow user to identify in Tcl which cell is implemented as LUT Ram and which is implemented as EBR ram. 04/10/2025: Per Joginder, deferred to 2025.2. | Joginder Singh |  |  |  |  | orange | 10%
Online Help Reference Guides | Tcl Command Reference Guide | Accessing Command Help and Command Options in the Tcl Console | Ave Manriquez | [6 empty] | white | 30%
Online Help Reference Guides | Tcl Command Reference Guide | Accessing Command Help and Command Options in the Tcl Console | Adel Jambalos | [6 empty] | white | 30%
Online Help Reference Guides | Tcl Command Reference Guide | Accessing Command Help and Command Options in the Tcl Console | Ruby-Ann Daliva | [6 empty] | white | 30%
Online Help Reference Guides | Tcl Command Reference Guide | Accessing Command Help and Command Options in the Tcl Console | Verna Deatras | [6 empty] | white | 30%
Online Help Reference Guides | Tcl Command Reference Guide | Creating and Running Custom Tcl Scripts | Ave Manriquez | [6 empty] | white | 30%
Online Help Reference Guides | Tcl Command Reference Guide | Creating and Running Custom Tcl Scripts | Adel Jambalos | [6 empty] | white | 30%
Online Help Reference Guides | Tcl Command Reference Guide | Creating and Running Custom Tcl Scripts | Ruby-Ann Daliva | [6 empty] | white | 30%
Online Help Reference Guides | Tcl Command Reference Guide | Creating and Running Custom Tcl Scripts | Verna Deatras | [6 empty] | white | 30%
Online Help Reference Guides | Tcl Command Reference Guide | Running Tcl Scripts When Launching the Radiant Software | Adel Jambalos | [6 empty] | white | 30%
Online Help Reference Guides | Tcl Command Reference Guide | Radiant Software Tool Tcl Command Syntax | Ruby-Ann Daliva | •ERD-17.08 (DNG-22406) – Request for Power Calculator to be verbose about why changes are rejected--ECN_YES_TO_DEFERERD DNG-22520 •ERD-19.04 (DNG-22520) TCL Command : Enhancements for IP Management - Catalog List---Verified to the Reporter (Matthew H.), NO documentation needed | Qinhai Zhang/Joginder Singh |  |  |  |  | yellow | 50%
Standalone Tools online help | Stand-Alone Programmer |  | Verna Deatras | [6 empty] | white | 30%
Standalone Tools online help | Stand-Alone Programmer |  | Ave Manriquez | [6 empty] | white | 30%
Standalone Tools online help | Stand-Alone Reveal |  | Ruby-Ann Daliva | [6 empty] | white | 30%
Standalone Tools online help | Stand-Alone Reveal |  | Adel Jambalos | [6 empty] | white | 30%
Standalone Tools online help | Stand-Alone Reveal |  | Ave Manriquez | [6 empty] | white | 30%
Standalone Tools online help | Stand-Alone Reveal |  | Verna Deatras | [6 empty] | white | 30%
Standalone Tools online help | Stand-Alone Power Estimator | [8 empty] | white | 30%
Standalone Tools online help | EPIC |  | Verna Deatras | [6 empty] | white | 30%
PDF Documents | Radiant Migration from Diamond Guide |  | Verna Deatras | [6 empty] | white | 30%
PDF Documents | Radiant Migration from iCECube2 |  | Verna Deatras | [6 empty] | white | 30%
PDF Documents | Radiant Tutorial | All | Verna Deatras | [6 empty] | white | 30%
PDF Documents | Block Based Design Tutorial |  | Ruby-Ann Daliva | [6 empty] | white | 30%
PDF Documents | Post-Synthesis Reveal Debug Flow Tutorial |  | Ruby-Ann Daliva | [6 empty] | white | 30%
PDF Documents | Lattice Intellectual Property User Guide |  | Ruby-Ann Daliva | [6 empty] | white | 30%
PDF Documents | Radiant LSE User Guide | [8 empty] | white | 30%
PDF Documents | Programming Tools User Guide |  | Ruby-Ann Daliva | [6 empty] | white | 30%
PDF Documents | Radiant User Guide |  | Ruby-Ann Daliva | [6 empty] | white | 30%
PDF Documents | PDF Version of Online Help |  | Verna Deatras | [6 empty] | white | 30%
PDF Documents | Reveal User Guide |  | Ruby-Ann Daliva | [6 empty] | white | 30%
PDF Documents | Reveal Troubleshooting Guide | All | Ruby-Ann Daliva | [6 empty] | white | 30%
PDF Documents | Synopsys docs | [8 empty] | white | 30%
PDF Documents | ModelSim docs | [8 empty] | white | 30%
PDF Documents | Installation Guide-Windows | [8 empty] | white | 30%
PDF Documents | Installation Guide-Linux | All | [7 empty] | white | 30%
PDF Documents | Release Notes | All | Ave Manriquez | Device (Licensed) •ERD-03.20 (DNG-23935) – MachXO5-55TDQ device support (Controlled) •ERD-03.09 (DNG-23739) – Avant-E70B (02C) PSR Support (Licensed) •ERD-03.13 (DNG-23734) – Avant-E30B (01A) PSR Support (Licensed) Device (GA) •ERD-03.07 (DNG-23752) – LN2-MH 20 (GX30 02A) Support Requirements for Radiant 2025.1 •ERD-03.10 (DNG-23738) – Avant E/G/X70 (02C) Device Support •ERD-03.14 (DNG-23737) – Avant E30 (01A) Device Support •ERD-03.15 (DNG-23736) – Avant E/G/X 30 (02A) Device Support •ERD-03.11 (DNG-23735) – Avant-E 70/50 ES2 (03A) Device Support •ERD-03.16 (DNG-23725) – Double-NX Certus-NX Device Support Requirements for Radiant 2025.1 •ERD-03.02 (DNG-23724) – J10 Certus-NX Device Support Requirements for Radiant 2025.1 •ERD-03.06 (DNG-23722) – LN2-CT 20 (GX30 02A) Support Requirements for Radiant 2025.1 •ERD-03.05 (DNG-23716) – Mach-KH (E30 01A) Device Support Requirements for R2025.1 •ERD-16.01 (DNG-23439) – OS Support Requirements for 2025.1 Release •ERD-03.01 (DNG-23224) – J10 Mach Device Support Requirements for Radiant 2025.1 (ES & GA) •ERD-03.04 (DNG-23223) – Certus-KH Device (E30 01A) Support Requirements for R2025.1 •ERD-03.12 (DNG-23222) – Avant G/X 70/50 ES1 (03A) Device Support •ERD-03.22 (DNG-22586) – Pin Migration support for MachXO5 family •ERD-03.16 (DNG-23725) – Double-NX Certus-NX Device Support Requirements for Radiant 2025.1 •ERD-03.02 (DNG-23724) – J10 Certus-NX Device Support Requirements for Radiant 2025.1 •ERD-03.06 (DNG-23722) – LN2-CT 20 (GX30 02A) Support Requirements for Radiant 2025.1 •ERD-19.04 (DNG-22520) – TCL Command: Enhancements for IP Management - Catalog List--not visible for Release Notes •ERD-19.06 (DNG-22239) – Allow user to identify in Tcl which cell is implemented as LUT ram and which is implemented as EBR ram. •ERD-17.01 (DNG-22850) – Power Calculator DPM use model not clear--added in Release Notes •ERD-17.02 (DNG-22745) – Power Calculator tool tip on 0 MHz clock entries--not visible for Release Notes •ERD-17.04 (DNG-22642) – Power calculator should make user entry of IO banks optional •ERD -17.05 (DNG-22640) – Simplify the entry of PLL data in PWC •ERD-17.07 (DNG-22519) – Power Calculator: Request for better clock frequency handling •ERD-17.08 (DNG-22406) – Request for Power Calculator to be verbose about why changes are rejected | [5 empty] | yellow | 50%
PDF Documents | Release Notes | All | Adel Jambalos | Device (Licensed) •ERD-03.20 (DNG-23935) – MachXO5-55TDQ device support (Controlled) •ERD-03.09 (DNG-23739) – Avant-E70B (02C) PSR Support (Licensed) •ERD-03.13 (DNG-23734) – Avant-E30B (01A) PSR Support (Licensed) Device (GA) •ERD-03.07 (DNG-23752) – LN2-MH 20 (GX30 02A) Support Requirements for Radiant 2025.1 •ERD-03.10 (DNG-23738) – Avant E/G/X70 (02C) Device Support •ERD-03.14 (DNG-23737) – Avant E30 (01A) Device Support •ERD-03.15 (DNG-23736) – Avant E/G/X 30 (02A) Device Support •ERD-03.11 (DNG-23735) – Avant-E 70/50 ES2 (03A) Device Support •ERD-03.16 (DNG-23725) – Double-NX Certus-NX Device Support Requirements for Radiant 2025.1 •ERD-03.02 (DNG-23724) – J10 Certus-NX Device Support Requirements for Radiant 2025.1 •ERD-03.06 (DNG-23722) – LN2-CT 20 (GX30 02A) Support Requirements for Radiant 2025.1 •ERD-03.05 (DNG-23716) – Mach-KH (E30 01A) Device Support Requirements for R2025.1 •ERD-16.01 (DNG-23439) – OS Support Requirements for 2025.1 Release •ERD-03.01 (DNG-23224) – J10 Mach Device Support Requirements for Radiant 2025.1 (ES & GA) •ERD-03.04 (DNG-23223) – Certus-KH Device (E30 01A) Support Requirements for R2025.1 •ERD-03.12 (DNG-23222) – Avant G/X 70/50 ES1 (03A) Device Support •ERD-03.22 (DNG-22586) – Pin Migration support for MachXO5 family •ERD-03.16 (DNG-23725) – Double-NX Certus-NX Device Support Requirements for Radiant 2025.1 •ERD-03.02 (DNG-23724) – J10 Certus-NX Device Support Requirements for Radiant 2025.1 •ERD-03.06 (DNG-23722) – LN2-CT 20 (GX30 02A) Support Requirements for Radiant 2025.1 •ERD-19.04 (DNG-22520) – TCL Command: Enhancements for IP Management - Catalog List--not visible for Release Notes •ERD-19.06 (DNG-22239) – Allow user to identify in Tcl which cell is implemented as LUT ram and which is implemented as EBR ram. •ERD-17.01 (DNG-22850) – Power Calculator DPM use model not clear--added in Release Notes •ERD-17.02 (DNG-22745) – Power Calculator tool tip on 0 MHz clock entries--not visible for Release Notes •ERD-17.04 (DNG-22642) – Power calculator should make user entry of IO banks optional •ERD -17.05 (DNG-22640) – Simplify the entry of PLL data in PWC •ERD-17.07 (DNG-22519) – Power Calculator: Request for better clock frequency handling •ERD-17.08 (DNG-22406) – Request for Power Calculator to be verbose about why changes are rejected | [5 empty] | yellow | 50%
PDF Documents | Release Notes | All | Ruby-Ann Daliva | Device (Licensed) •ERD-03.20 (DNG-23935) – MachXO5-55TDQ device support (Controlled) •ERD-03.09 (DNG-23739) – Avant-E70B (02C) PSR Support (Licensed) •ERD-03.13 (DNG-23734) – Avant-E30B (01A) PSR Support (Licensed) Device (GA) •ERD-03.07 (DNG-23752) – LN2-MH 20 (GX30 02A) Support Requirements for Radiant 2025.1 •ERD-03.10 (DNG-23738) – Avant E/G/X70 (02C) Device Support •ERD-03.14 (DNG-23737) – Avant E30 (01A) Device Support •ERD-03.15 (DNG-23736) – Avant E/G/X 30 (02A) Device Support •ERD-03.11 (DNG-23735) – Avant-E 70/50 ES2 (03A) Device Support •ERD-03.16 (DNG-23725) – Double-NX Certus-NX Device Support Requirements for Radiant 2025.1 •ERD-03.02 (DNG-23724) – J10 Certus-NX Device Support Requirements for Radiant 2025.1 •ERD-03.06 (DNG-23722) – LN2-CT 20 (GX30 02A) Support Requirements for Radiant 2025.1 •ERD-03.05 (DNG-23716) – Mach-KH (E30 01A) Device Support Requirements for R2025.1 •ERD-16.01 (DNG-23439) – OS Support Requirements for 2025.1 Release •ERD-03.01 (DNG-23224) – J10 Mach Device Support Requirements for Radiant 2025.1 (ES & GA) •ERD-03.04 (DNG-23223) – Certus-KH Device (E30 01A) Support Requirements for R2025.1 •ERD-03.12 (DNG-23222) – Avant G/X 70/50 ES1 (03A) Device Support •ERD-03.22 (DNG-22586) – Pin Migration support for MachXO5 family •ERD-03.16 (DNG-23725) – Double-NX Certus-NX Device Support Requirements for Radiant 2025.1 •ERD-03.02 (DNG-23724) – J10 Certus-NX Device Support Requirements for Radiant 2025.1 •ERD-03.06 (DNG-23722) – LN2-CT 20 (GX30 02A) Support Requirements for Radiant 2025.1 •ERD-19.04 (DNG-22520) – TCL Command: Enhancements for IP Management - Catalog List--not visible for Release Notes •ERD-19.06 (DNG-22239) – Allow user to identify in Tcl which cell is implemented as LUT ram and which is implemented as EBR ram. •ERD-17.01 (DNG-22850) – Power Calculator DPM use model not clear--added in Release Notes •ERD-17.02 (DNG-22745) – Power Calculator tool tip on 0 MHz clock entries--not visible for Release Notes •ERD-17.04 (DNG-22642) – Power calculator should make user entry of IO banks optional •ERD -17.05 (DNG-22640) – Simplify the entry of PLL data in PWC •ERD-17.07 (DNG-22519) – Power Calculator: Request for better clock frequency handling •ERD-17.08 (DNG-22406) – Request for Power Calculator to be verbose about why changes are rejected | [5 empty] | yellow | 50%
PDF Documents | Release Notes | All | Verna Deatras | Device (Licensed) •ERD-03.20 (DNG-23935) – MachXO5-55TDQ device support (Controlled) •ERD-03.09 (DNG-23739) – Avant-E70B (02C) PSR Support (Licensed) •ERD-03.13 (DNG-23734) – Avant-E30B (01A) PSR Support (Licensed) Device (GA) •ERD-03.07 (DNG-23752) – LN2-MH 20 (GX30 02A) Support Requirements for Radiant 2025.1 •ERD-03.10 (DNG-23738) – Avant E/G/X70 (02C) Device Support •ERD-03.14 (DNG-23737) – Avant E30 (01A) Device Support •ERD-03.15 (DNG-23736) – Avant E/G/X 30 (02A) Device Support •ERD-03.11 (DNG-23735) – Avant-E 70/50 ES2 (03A) Device Support •ERD-03.16 (DNG-23725) – Double-NX Certus-NX Device Support Requirements for Radiant 2025.1 •ERD-03.02 (DNG-23724) – J10 Certus-NX Device Support Requirements for Radiant 2025.1 •ERD-03.06 (DNG-23722) – LN2-CT 20 (GX30 02A) Support Requirements for Radiant 2025.1 •ERD-03.05 (DNG-23716) – Mach-KH (E30 01A) Device Support Requirements for R2025.1 •ERD-16.01 (DNG-23439) – OS Support Requirements for 2025.1 Release •ERD-03.01 (DNG-23224) – J10 Mach Device Support Requirements for Radiant 2025.1 (ES & GA) •ERD-03.04 (DNG-23223) – Certus-KH Device (E30 01A) Support Requirements for R2025.1 •ERD-03.12 (DNG-23222) – Avant G/X 70/50 ES1 (03A) Device Support •ERD-03.22 (DNG-22586) – Pin Migration support for MachXO5 family •ERD-03.16 (DNG-23725) – Double-NX Certus-NX Device Support Requirements for Radiant 2025.1 •ERD-03.02 (DNG-23724) – J10 Certus-NX Device Support Requirements for Radiant 2025.1 •ERD-03.06 (DNG-23722) – LN2-CT 20 (GX30 02A) Support Requirements for Radiant 2025.1 •ERD-19.04 (DNG-22520) – TCL Command: Enhancements for IP Management - Catalog List--not visible for Release Notes •ERD-19.06 (DNG-22239) – Allow user to identify in Tcl which cell is implemented as LUT ram and which is implemented as EBR ram. •ERD-17.01 (DNG-22850) – Power Calculator DPM use model not clear--added in Release Notes •ERD-17.02 (DNG-22745) – Power Calculator tool tip on 0 MHz clock entries--not visible for Release Notes •ERD-17.04 (DNG-22642) – Power calculator should make user entry of IO banks optional •ERD -17.05 (DNG-22640) – Simplify the entry of PLL data in PWC •ERD-17.07 (DNG-22519) – Power Calculator: Request for better clock frequency handling •ERD-17.08 (DNG-22406) – Request for Power Calculator to be verbose about why changes are rejected | [5 empty] | yellow | 50%
PDF Documents |  |  | Ave Manriquez | •ERD-13.01 (DNG-23102) – SSPI Command Line Tool •ERD-13.08 (DNG-23431) – J10D support for image signing and ESFB manifest signing •ERD 12.01 (DNG-22647) – Enhance the Reveal controller GUI for LEDs •ERD 16.01 (DNG-23439) – OS support requirements for 2025.1 Release •ERD-14.01 (DNG-22523) – Provide Synplify Lattice Edition User Guides on Lattice web | [5 empty] | yellow | 50%
PDF Documents |  |  | Adel Jambalos | •ERD-13.01 (DNG-23102) – SSPI Command Line Tool •ERD-13.08 (DNG-23431) – J10D support for image signing and ESFB manifest signing •ERD 12.01 (DNG-22647) – Enhance the Reveal controller GUI for LEDs •ERD 16.01 (DNG-23439) – OS support requirements for 2025.1 Release •ERD-14.01 (DNG-22523) – Provide Synplify Lattice Edition User Guides on Lattice web | [5 empty] | yellow | 50%
PDF Documents |  |  | Ruby-Ann Daliva | •ERD-13.01 (DNG-23102) – SSPI Command Line Tool •ERD-13.08 (DNG-23431) – J10D support for image signing and ESFB manifest signing •ERD 12.01 (DNG-22647) – Enhance the Reveal controller GUI for LEDs •ERD 16.01 (DNG-23439) – OS support requirements for 2025.1 Release •ERD-14.01 (DNG-22523) – Provide Synplify Lattice Edition User Guides on Lattice web | [5 empty] | yellow | 50%
PDF Documents |  |  | Verna Deatras | •ERD-13.01 (DNG-23102) – SSPI Command Line Tool •ERD-13.08 (DNG-23431) – J10D support for image signing and ESFB manifest signing •ERD 12.01 (DNG-22647) – Enhance the Reveal controller GUI for LEDs •ERD 16.01 (DNG-23439) – OS support requirements for 2025.1 Release •ERD-14.01 (DNG-22523) – Provide Synplify Lattice Edition User Guides on Lattice web | [5 empty] | yellow | 50%
PDF Documents | Release Notes | Known Issues | Ave Manriquez | Add Known Issues | [5 empty] | white | 30%
PDF Documents | Release Notes | Known Issues | Adel Jambalos | Add Known Issues | [5 empty] | white | 30%
PDF Documents | Release Notes | Known Issues | Ruby-Ann Daliva | Add Known Issues | [5 empty] | white | 30%
PDF Documents | Release Notes | Known Issues | Verna Deatras | Add Known Issues | [5 empty] | white | 30%
PDF Documents | Update HTML page |  | Ruby-Ann Daliva | [6 empty] | white | 30%
PDF Documents | Readme |  | Ave Manriquez | [6 empty] | white | 30%
PDF Documents | Readme |  |  | PARTIAL | [5 empty] | white | 30%
PDF Documents | Readme |  | Verna Deatras | ERD-03.08 DNG-22303 Mach-XO4 Support (Phase 1) ERD - Partial for EAPR | [5 empty] | white | 30%
PDF Documents | Readme |  | Adel Jambalos | ERD-05.05 DNG-20141 Compilation Result and Info In Tabular Form [Adel] 06-04-2005 Checked by SME, for verification in JIRA. User Guides > Managing Projects > Viewing Logs and Reports. | [5 empty] | green | 100%
PDF Documents | Readme |  | Ruby-Ann Daliva | ERD-08.01 DNG-23048 Automatically add jitter timing requirement for Nexus--05/15/2025: Sent draft for approval; 05/23/2025: per Gebre, We haven't landed on a final name yet. Original implementation was and still is generate_uncertainty. | [5 empty] | white | 30%
PDF Documents | Readme |  | Verna Deatras | ERD-09.06 Support post par reveal flow 05/13/2025 -- Done. Added content provided by Pradeep: User Guides > Testing and Debugging On-Chip > About Reveal Logic Analysis > Post-PAR Reveal Incremental Flow Sent for review | [5 empty] | green | 100%
PDF Documents | Readme |  | Ave Manriquez | ERD-10.03 DNG-22262 Allow user to specify Verilog/VHDL version on a file basis (Synplify) 05/23/2025: Per Phil, same with DNG-26495 - no documentation support needed as this is for future release. | [5 empty] | white | 30%
PDF Documents | Readme |  | Adel Jambalos | ERD-13.05 DNG-22428 Support for various MRAM in Radiant Programmer for QSPI mode Config [Adel] 06-04-2005 - MRAM devices added. Please verify in User Guides > Programming the FPGA > SPI Flash Support | [5 empty] | green | 100%
PDF Documents | Readme |  |  | ECN | [5 empty] | white | 30%
PDF Documents | Readme |  | Adel Jambalos | DNG-23751 JTAGMON support (subtask - DNG-26663 JTAGMON Documentation Support [Adel] - 06-04-2025 Done. Ready for QA verification: User Guides > Testing and Debugging On-Chip > Using JTAGMON [Verna] - Completed primitives | [5 empty] | green | 100%
PDF Documents | Readme |  | Verna Deatras | DNG-23751 JTAGMON support (subtask - DNG-26663 JTAGMON Documentation Support [Adel] - 06-04-2025 Done. Ready for QA verification: User Guides > Testing and Debugging On-Chip > Using JTAGMON [Verna] - Completed primitives | [5 empty] | green | 100%

## radiant_docu
Radiant Documentation
Online Help User Guides
Online Help Reference
Standalone Tools
PDF Documents

## New docs
New Major Documentation
Lead | Projects | Support | SME
Verna | MachXO4 Primitives List (with support from the team) | Ave | Bo Wang
Verna | MachXO4 Primitives List (with support from the team) | Adel | Bo Wang
Verna | MachXO4 Primitives List (with support from the team) | Ry | Bo Wang
Verna | MachXO4D | Ave | Bo Wang
Verna | MachXO4D | Adel | Bo Wang
Verna | MachXO4D | Ry | Bo Wang
Verna | Migration User Guide | Ave | Bo Wang
Adel | TCL Dedicated User Guide | Ry | Joginder Singh Qinhai
Ry | Low Power Reduction
| ENR-01.01 DNG-24867 - LSE for Low Power Reduction | Ry | Jun Zhao Chin Hsiung Shen
| ENR-01.04 DNG-24871 - Require Synplify for supporting low power goal. | Ry | Jun Zhao Chin Hsiung Shen
| ENR-01.03 DNG-25007 - GUI for Low Power Reduction | Verna | Jun Zhao Chin Hsiung Shen
| ENR-02.01 DNG-24987 - Radiant 2025.1 Porting AP to Jedi | Verna | Jun Zhao Chin Hsiung Shen
| ENR-01.05 DNG-24870 - Power calculator for supporting low power goal. | Adel | Jun Zhao Chin Hsiung Shen
| ENR-03.0 DNG-25079 - Integrate physical synthesis tool to PAR | Adel | Jun Zhao Chin Hsiung Shen
| ENR-01.02 DNG-24868 - Map for Low Power Reduction | Ave | Jun Zhao Chin Hsiung Shen
Verna | DNG-23432 [R2025.1 MRD-13.09] MachXO5-55TDQ image signing with PQC algorithms | Need to document under XO5 Secure Control Pack
| DNG-25439 Subscription Licensing Page Guidelines |  | Mahj Leoparte

## ECNs
1. DNG-24010 Request to block bitgen to proceed when Encryption + Compression is enabled
2. DNG-23780 Require Enhancing Radiant GUI to support Early IO Encryption for Authentication-Only bitstream